## Risk Scale
Scale: 1 - 5
Probability | Description
1 | Unlikely to happen during the project
2 | May happen once before delivery deadline
3 | Expected to happen at least once
4 | Might happen more than once
5 | High chance of happening multiple times
Impact | Description
1 | Will require slight readjustment of work plan
2 | Will require readjustment of work plan
3 | Project scope will have to be readjustment
4 | Focus of project will have to change
5 | We will have to start a new project

## Risk Assessment V1 29112022
ID | Risk Area | Risk Description | Probability | Impact | Risk Factor | Proactive Mitigation | Reactive Mitigation | Follow-up | Status Date | Follow-up Date | Status
R3 | Tech Stack | Different tech stack technologies might not work well together. | 5 | 2 | 10 | Thoroughly research all desired parts of the tech stack to ensure they have proper interfaces. | Find a replacement for the specific part of the tech stack. | Planned date | 2022-11-29 | 2022-11-30 | Initial
R4 | Tools | License to development/design software expires. | 2 | 3 | 6 | Check all desired software tools and make sure no licenses are required or will expire before 21/12/2022 | Renew license through non-monetary means if possible. Otherwise find a replacement software ASAP | Planned date | 2022-11-29 | 2022-11-30 | Initial
R2 | Application | The application is hard to test because of highly-coupled code. | 2 | 2 | 4 | Follow framework guidelines & review each others code to ensure responsibility of code parts is properly separated. | Reduce high coupling by having another team member fix the problems. | On impact | 2022-11-29 |  | Inital
R1 | Team | Team member leaves the project | 1 | 4 | 4 | Make sure everyone on the team is happy and engaged. Keep toxicity low. | Find a replacement OR Continue with one less member. | On impact | 2022-11-29 |  | Intial
R5 | Tools | Riot Games API is an external dependency and might be subject to major changes / shut down. | 1 | 5 | 5 | Stay up to date with Riot Games to make sure massive changes won't be implemented / it won't be shut down. | Make sure what can be salvaged from the project to fit the use case for another/similar game. | On impact | 2022-11-29 |  | Inital
R6 | Tools | Riot Games API is an external dependency and might be subject to minor to moderate changes. | 2 | 2 | 4 | Stay up to date with changes to the API via new documentation and consulting experts (Discord). Make system robust to sudden changes in Riot Games' API. | Read up on possible new documentation, consult Riot Games API experts (Discord) and implement needed changes | On impact | 2022-11-29 |  | Initial
R7 | Tools | Team members have different development environments which can result in difficulties´. | 5 | 2 | 10 | Implement a containerized environment (Docker), have extensive readme, have a sample .env file. | Collaborate to find dev environment differences and eliminate them. | Planned date | 2022-11-29 | 2022-11-30 | Initial
R8
R9
R10
R11
R12
R13
R14
R15
R16
R17

## Risk Matrix V1 29112022
Impact
|  | 1 | 2 | 3 | 4 | 5
Probability | 5 |  | R3, R7
4
| 3 |  | R6
| 2 |  | R2 | R4
| 1 |  |  |  | R1 | R5

## Risk Assessment V2 30112022
ID | Risk Area | Risk Description | Probability | Impact | Risk Factor | Proactive Mitigation | Reactive Mitigation | Follow-up | Status Date | Follow-up Date | Status
R1 | Team | Team member leaves the project | 1 | 4 | 4 | Make sure everyone on the team is happy and engaged. Keep toxicity low. | Find a replacement OR Continue with one less member. | On impact | 2022-11-29 | Not planned | Intial
R2 | Application | The application is hard to test because of highly-coupled code. | 2 | 2 | 4 | Follow framework guidelines & review each others code to ensure responsibility of code parts is properly separated. | Reduce high coupling by having another team member fix the problems. | On impact | 2022-11-29 | Not planned | Inital
R3 | Tech Stack | Different tech stack technologies might not work well together. | 5 | 2 | 10 | Thoroughly research all desired parts of the tech stack to ensure they have proper interfaces. | Find a replacement for the specific part of the tech stack. | Planned date | 2022-11-29 | 2022-11-30 | Initial
|  |  | 1 | 2 | 2 | Thoroughly research new parts before they get added to make sure they have proper interfaces. | Find a replacement for the specific part of the tech stack. | On impact | 2022-11-30 | Not planned | All current parts have been confirmed to be compatible
R4 | Tools | License to development/design software expires. | 2 | 3 | 6 | Check all desired software tools and make sure no licenses are required or will expire before 21/12/2022 | Renew license through non-monetary means if possible. Otherwise find a replacement software ASAP | Planned date | 2022-11-29 | 2022-11-30 | Initial
|  |  | 1 | 3 | 3 | Check newly planned software to make sure no licenses are required or will expire before 21/12/2022 | Renew license through non-monetary means if possible. Otherwise find a replacement software ASAP | On impact | 2022-11-30 | Not planned | All current software has been confirmed to not require licenses. Required licenses will not expire before 21/12/2022
R5 | Tools | Riot Games API is an external dependency and might be subject to major changes / shut down. | 1 | 5 | 5 | Stay up to date with Riot Games to make sure massive changes won't be implemented / it won't be shut down. | Make sure what can be salvaged from the project to fit the use case for another/similar game. | On impact | 2022-11-29 |  | Initial
R6 | Tools | Riot Games API is an external dependency and might be subject to minor to moderate changes. | 2 | 2 | 4 | Stay up to date with changes to the API via new documentation and consulting experts (Discord). Make system robust to sudden changes in Riot Games' API. | Read up on possible new documentation, consult Riot Games API experts (Discord) and implement needed changes | On impact | 2022-11-29 |  | Initial
|  |  | 2 | 2 | 4 | Implement mocking of Riot Games API for unit testing to isolate system related errors and Riot Games API related errors. | Read up on possible new documentation, consult Riot Games API experts (Discord) and implement needed changes | When implemented | 2022-11-30 |  | We've made a plan to implement mocking of the Riot Games API for unit testing to isolate system related errors and Riot Games API related errors.
R7 | Tools | Team members have different development environments which can result in difficulties´. | 5 | 2 | 10 | Implement a containerized environment (Docker), have extensive readme, have a sample .env file. | Collaborate to find dev environment differences and eliminate them. | Planned date | 2022-11-29 | 2022-11-30 | Initial
|  |  | 2 | 2 | 4 | Make sure to update sample .env file and readme. | Collaborate to find dev environment differences and eliminate them. | On impact | 2022-11-30 | Not planned | System has been dockerized, sample .env added and readme added.

## Risk Matrix V2 30112022
Impact
|  | 1 | 2 | 3 | 4 | 5
Probability | 5
4
3
| 2 |  | R2, R6, R7
| 1 |  | R3 | R4 | R1 | R5

## Risk Assessment V3 10122022
ID | Risk Area | Risk Description | Probability | Impact | Risk Factor | Proactive Mitigation | Reactive Mitigation | Follow-up | Status Date | Follow-up Date | Status
R1 | Team | Team member leaves the project | 1 | 4 | 4 | Make sure everyone on the team is happy and engaged. Keep toxicity low. | Find a replacement OR Continue with one less member. | On impact | 2022-11-29 | Not planned | Intial
R2 | Application | The application is hard to test because of highly-coupled code. | 2 | 2 | 4 | Follow framework guidelines & review each others code to ensure responsibility of code parts is properly separated. | Reduce high coupling by having another team member fix the problems. | On impact | 2022-11-29 | Not planned | Inital
R3 | Tech Stack | Different tech stack technologies might not work well together. | 5 | 2 | 10 | Thoroughly research all desired parts of the tech stack to ensure they have proper interfaces. | Find a replacement for the specific part of the tech stack. | Planned date | 2022-11-29 | 2022-11-30 | Initial
|  |  | 1 | 2 | 2 | Thoroughly research new parts before they get added to make sure they have proper interfaces. | Find a replacement for the specific part of the tech stack. | On impact | 2022-11-30 | Not planned | All current parts have been confirmed to be compatible
R4 | Tools | License to development/design software expires. | 2 | 3 | 6 | Check all desired software tools and make sure no licenses are required or will expire before 21/12/2022 | Renew license through non-monetary means if possible. Otherwise find a replacement software ASAP | Planned date | 2022-11-29 | 2022-11-30 | Initial
|  |  | 1 | 3 | 3 | Check newly planned software to make sure no licenses are required or will expire before 21/12/2022 | Renew license through non-monetary means if possible. Otherwise find a replacement software ASAP | On impact | 2022-11-30 | Not planned | All current software has been confirmed to not require licenses. Required licenses will not expire before 21/12/2022
R5 | Tools | Riot Games API is an external dependency and might be subject to major changes / shut down. | 1 | 5 | 5 | Stay up to date with Riot Games to make sure massive changes won't be implemented / it won't be shut down. | Make sure what can be salvaged from the project to fit the use case for another/similar game. | On impact | 2022-11-29 | Not planned | Initial
R6 | Tools | Riot Games API is an external dependency and might be subject to minor to moderate changes. | 2 | 2 | 4 | Stay up to date with changes to the API via new documentation and consulting experts (Discord). Make system robust to sudden changes in Riot Games' API. | Read up on possible new documentation, consult Riot Games API experts (Discord) and implement needed changes | On impact | 2022-11-29 | Not planned | Initial
|  |  | 2 | 2 | 4 | Implement mocking of Riot Games API for unit testing to isolate system related errors and Riot Games API related errors. | Read up on possible new documentation, consult Riot Games API experts (Discord) and implement needed changes | When implemented | 2022-11-30 | Not planned | We've made a plan to implement mocking of the Riot Games API for unit testing to isolate system related errors and Riot Games API related errors.
|  |  | 2 | 1 | 2 | Stay up to date with changes to the API via new documentation and consulting experts (Discord). Make system robust to sudden changes in Riot Games' API. | Read up on possible new documentation, consult Riot Games API experts (Discord) and implement needed changes | On impact | 2022-12-10 | Not planned | Riot Games API has been mocked in all related unit tests.
R7 | Tools | Team members have different development environments which can result in difficulties´. | 5 | 2 | 10 | Implement a containerized environment (Docker), have extensive readme, have a sample .env file. | Collaborate to find dev environment differences and eliminate them. | Planned date | 2022-11-29 | 2022-11-30 | Initial
|  |  | 2 | 2 | 4 | Make sure to update sample .env file and readme. | Collaborate to find dev environment differences and eliminate them. | On impact | 2022-11-30 | Not planned | System has been dockerized, sample .env added and readme added.

## Risk Matrix V3 10122022
Impact
|  | 1 | 2 | 3 | 4 | 5
Probability | 5
4
3
| 2 | R6 | R2, R7
| 1 |  | R3 | R4 | R1 | R5